## Project Planner
Boulder Apple Tree Project Planner
Blue: Stage 1, Orange: Stage 2, Cyan: Stage 3, Purple: Stage 4 |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Create visual design | 1 | 2 | 1 | 1 | 100%
Adjust visual design to sponsor feedback | 2 | 1 | 2 | 1 | 100%
Sketch out all required app’s functions | 3 | 2 | 3 | 2 | 100%
Discuss with sponsor about design of functionality for app | 4 | 1 | 4 | 1 | 100%
Main Menu Created | 5 | 3 | 5 | 3 | 85%
Database Creation | 5 | 3 | 5 | 3 | 85%
Input individual tree measurements | 6 | 1 | 6 | 1 | 80%
Input Orchard Measurements | 6 | 1 | 6 | 1 | 80%
Photo functionality | 7 | 5 | 8 | 5 | 30%
Save Measurements to Database/Upload | 6 | 5 | 6 | 5 | 80%
Create Graphics (if needed) | 8 | 7 | 9 | 7 | 40%
User authentication and registration implemented | 5 | 5 | 5 | 5 | 80%
Test if app located accurate position | 10 | 5 | n/a | n/a | n/a
Test if app updates correct information | 10 | 3 | n/a | n/a | n/a
Test for offline functionality | 10 | 5 | n/a | n/a | n/a
Test user authentication method | 10 | 2 | n/a | n/a | n/a
Finish final project report | 20 | 3 | n/a | n/a | n/a
A demo for the app that shows functions | 15 | 4 | n/a | n/a | n/a
Include videos of operating the app | 19 | 1 | n/a | n/a | n/a